## Slide 1
SA-SAMS Modernisation Programme
Issue 4: Monthly Progress Report as of July 2023
Let us Catch Up
The project obtained approval from the key decision-making structures of the DBE to proceed with the revised pilot approach. This will ensure all provinces are actively involved in the soft launch testing and build capacity for technical and functional support. To ensure the success of this pilot, The provincial EMIS teams are working closely with the project team to determine the ICT readiness of the pilot schools.
Release 1 and 2 (School and Learner Management) training was completed for Mpumalanga on 25-26 July 2023. The Project Executive will have a meeting with Western Cape HoD and his Team to map the way-forward for training to be held in the province.
Noticeable progress has been made on modernized solution for the Human Resource (Release 3), School and Learner modules.
The Release 3 Human Resources functionality will be deployed in the sandpit on 11 August 2023 and the training of the superusers will commence thereafter on dates still to be determined in August.
In Progress
Coming Soon …
Business Analysis & Process Improvement
Review and walkthrough of Manage School functional requirement specification (FRS).
DBE Signoff of FRS - Manage Human Resources.
DBE Signoff of FRS – Manage Learner.
DBE Signoff of FRS – User Role Matrix: MS, ML, MHR, System Admin
Planning for Curriculum module workshops.
Analysis of the current SA-SAMS Curriculum Module.
Development, Data & Deployment
Development of outstanding School and Learner features.
Finalise new DevOps Framework/Processes for weekly deployments to ensure more rapid delivery of the software.
Document Data Strategy.
Architecture, Infrastructure & Testing
Supporting DBE with:
  DBE finalising signoff of User Acceptance Testing for Release 1 & 2.
  UAT Scripts for Release 3.
  Supporting the DBE to finalise the proposal from SITA for cloud hosting, capacity building and testing.
System Integration Testing for Release 3
  Finalised Test Execution for Manage Human Resources.
Retest outstanding defects for School, Learner, and Human Resources modules.
Readied UAT Infrastructure environment.
Signoff of Release 3 Test Plan.
Change Management & Training
All provinces are now participating in bi-weekly pilot progress meeting.
A monitoring and tracking template has been developed and will be shared with the provinces to track change management, training, and communications.
Develop new Pilot Approach Training Strategy.
Release 3 training preparation, design and definition, and co-ordination.
Months Achievements
Completed : Phase 1: DBE Walkthrough for Manage Human Resources FRS.
Completed : Phase 1: DBE Walkthrough for User Role Matrix (System Admin, MS, ML, MHR).
Completed : Phase 1: DBE Walkthrough for Manage Learner FRS.
Completed: Release 4: Manage Curriculum Business Analysis and Process Improvement workstream planning.
Completed MHR Development. Deployed MHR Development to SIT environment.
Completed: Release 3 Test Plan
Completed : SIT Testing : Signoff Test Scripts, Execution and Test Plan for Release 1 & 2.
Completed : Sandbox training on Release 1 & 2
Completed : System Integration Testing – Release 3: Completed Test Scripts, Execution and Test Plan, ready for finalization.
Completed: Cycle 1 defects logged for Release 3 (HR).
Completed: R1 and R2 training for Mpumalanga Province superusers
Completed: Updated the revised Change Management Strategy for the revised pilot approach.
The following project activities have been planned:
Release 1 and 2 close-off:
School Management Functional Requirements Sign-off – Aug 2023
Signoff User Acceptance Testing by DBE– Aug 2023
Release 3 milestones:
Sign off Manage School FRS – Aug 2023
Sign off Human Resources FRS – Aug 2023
Sign off User Roles Matrix (System Admin, MS, ML, MHR) – Aug 2023
Unit testing of School, Learner and HR modules – Aug 2023
Bug fixes for Release 3 – Aug 2023
Deploy School and Learner changes to SIT, Sandbox and UAT environments – Aug 2023
Deploy OpenEMIS Dashboard and Data Integrator and Data Manager – Aug 2023
Deployment of Release 3 to Sandbox – Aug 2023
User Acceptance Testing Scripts – Aug 2023
Logged Defects for MHR in SIT, before closing off obtain sign off – Aug 2023
System access for Superusers and training – Aug 2023
Signoff UAT Testing for R3 – Aug 2023
Signoff new Pilot Approach Training Strategy – Aug 2023
Release a Quarterly Newsletter on Release 1, 2, and 3 progress. – Aug 2023
Align communication and stakeholder engagements to follow-up on Release 3 milestone. – Aug 2023
Release 4 milestones:
Manage Curriculum: Document Curriculum and Assessment FRS – Aug-Sep 2023
Manage Curriculum: Development – Sep 2023
Testing Statistics : System Integration Testing