## Slide 1
SA-SAMS Modernisation Programme
Issue 2: Monthly Progress Report as of May 2023
Let us Catch Up
To accelerate the delivery of the project the DBE recommended, and PSC and NECT Board has accepted, a phased approach to the project, with Phase 1 focusing on all existing functionality in the current SA-SAMS. Thereafter, the modernization requirements will be addressed in Phase 2.
SA-SAMS Modernization PMO is fully capacitated for the Phase 1 of the Programme.
The Project is currently working on raising additional funding to complete the modernization journey in 2026.
Release 1 and 2 training in the North West, Eastern Cape, Gauteng, Free State, and Kwa-Zulu Natal provinces have been successfully completed, with positive feedback on the value of the modernized SA-SAMS systems from the users training. Limpopo, Northern Cape are planned for June 2023. We are still awaiting dates from Mpumalanga and Western Cape.
In Progress
Coming Soon …
Business Analysis & Process Improvement
Finalise the realignment of Manage School and Manage Learner with the scope change request.
Finalise Requirements Definition for Release 3 - Manage Human Resources (95% complete)
Development, Data & Deployment
Development of the Manage Human Resources module for Phase 1.
Finalise new DevOps Framework/Processes for weekly deployments to ensure more rapid delivery of the software.
Architecture, Infrastructure & Testing
Supporting DBE with:
DBE finalising signoff of UAT Scripts for Release 1& 2.
DBE finalising signoff of User Acceptance Testing for Release 1 & 2.
UAT Scripts for Release 3.
Supporting the DBE to finalise the proposal from SITA for cloud hosting, capacity building and testing.
System Integration Testing for Release 3
Finalise Test Scripts for Manage Human Resources.
Change Management & Training
Northern Cape and Limpopo Province Super-user training for Release 1 and 2 on June 5-6 and June 12-13 respectively.
Training Strategy & Plan updated with content for pilot approach.
Achievements To Date
Phase 1: Analysis and Design of Manage Human Resources module.
Phase 1 Release 4: Manage Curriculum Business Analysis and Process Improvement workstream planning completed.
Completed MS and ML Development – Manage School and Manage Learner additional attributes.
Completed MHR Development: Teaching vs Non-teaching indicator, Search, List and View Staff member and Add Staff Member.
SIT Testing : Completed & Signoff Test Scripts and Test Plan for Release 1 & 2.
System Integration Testing – Release 3: Completed draft Test Plan, ready for review.
Training of Provincial Superusers on Release 1 and 2 functionalities delivered physically to North West and Eastern Cape. To date only Northern Cape has received virtual training and physical training is on the cards for the month of June.
The following project activities have been planned:
Release 1 and 2 close-off:
School and Learner Management Functional Requirements Sign-off – June 2023
Deploy issue resolutions to Dev and full R1 and R2 deployment to SIT – July 2023
Fix the final issues on R1 and R2 – July 2023
Sandbox training for Release 1 & 2 – June 2023
Signoff User Acceptance Testing for DBE – June 2023
Release 3 milestones:
Sign off Human Resources Functional Requirements Specifications – June 2023
Deploy School and Learner changes to SIT and Sandbox environments – June 2023
System Integration Testing (HR) and User Acceptance Testing Scripts – June 2023
Migrate final HR SIT deployment to Sandpit for training – June 2023
Develop and signoff Test Strategy Document – June 2023
Develop and sign off new Pilot Approach Training Strategy – June 2023
Deploy technical environment for sandbox training – June 2023
System access for Superusers and training – Aug 2023
Release 4 milestones:
Manage Curriculum: Analysis and Design kick-off – June 2023